## Slide 1
ENGINEERING REVIEW
Platform rebuild complete
Development and production are now fully separated, every release goes through an approved pipeline, and the compromised production host has been rebuilt clean.
2
Isolated environments
Dev and production on independent servers, databases and storage
524K
Catalogue records
Migrated to the new production database with zero loss
1
Security incident
Cryptominer found on the old host — contained, rebuilt, hardened
TnC Pharmacy · September 2026
Notes: Headline: the platform is on a stable footing. Environments are separated, deployment is controlled, and the security problem on the old production server is resolved. The rest of the deck covers what shipped, what is in flight, and what comes next.

## Slide 2
What we delivered
Four workstreams, all now in production.
1
Separated environments
Development and production run on independent servers with their own databases, storage and credentials. Changes are proven on dev before any customer sees them.
2
Controlled releases
Every change is automatically type-checked and tested. Production deployments require named approval — nothing reaches customers unreviewed.
3
Security remediation
The previous production server was running a cryptominer with administrator access. It was destroyed, rebuilt hardened, and access locked to our CDN only.
4
Engineering handbook
The platform, its environments and its failure modes are documented, so a new developer becomes productive without depending on tribal knowledge.
Previously: one shared server, manual deployment, no rollback path, credentials held in the code repository.
Notes: Emphasise the contrast at the bottom. Before this work there was a single server doing everything, deployments were manual, and there was no safe way to test a change. That is what allowed the security incident to go unnoticed.

## Slide 3
Current phase
IN PROGRESS
Three workstreams that make the platform usable day to day — for customers and for the counter staff.
1
WhatsApp notifications
Order confirmations, prescription status and delivery updates delivered to the channel customers actually read, instead of email nobody opens.
Order and payment confirmations
Prescription approved or query raised
Dispatch and delivery updates
2
Support module
One place for every customer query raised from the app, with an owner and a history — so questions stop living in personal phones and WhatsApp threads.
Tickets raised from the app
Assignment and status tracking
Full conversation history
3
Pharmacist enhancements
Faster work at the retail counter: a cleaner prescription review queue and improved OCR extraction that removes manual re-typing.
Streamlined review queue
Better OCR match accuracy
Fewer clicks per order
WhatsApp messaging runs through AiSensy, already integrated and live in production for order events.
Notes: This is the phase currently underway. Point out that WhatsApp is not a new vendor decision — the integration already exists and is live for order events; we are extending it across the order lifecycle. The support module is the one that reduces operational load most directly.

## Slide 4
Phase 1 — payments and delivery
Six stages, each shippable on its own so value arrives before the whole programme finishes.
1
Foundations
Order and money data made reliable
2
Online payments
Razorpay for over-the-counter orders
3
Cash on delivery
Coverage check and cash reconciliation
4
Courier link-up
Labels, tracking, delivery updates
5
Prescription flow
Pharmacist approval before payment
6
Returns & reports
Refunds, settlement, finance export
Payments — Razorpay
Cards, UPI, net banking and wallets, plus cash on delivery from launch. Over-the-counter orders pay at checkout. Prescription orders pay only after a pharmacist has approved the items, so we never hold money for medicine we cannot lawfully supply.
Delivery — logistics aggregator
A single integration reaching many couriers nationally. Delivery coverage is checked while the customer is still choosing, not after they have paid, and tracking updates flow back automatically into order status.
Sequencing note: the money path and the delivery path are each proven separately before prescription approval couples them together.
Notes: Stage 1 is unglamorous but non-negotiable: order amounts are currently stored as text, which cannot be reconciled against a payment gateway. It ships alone. Stages 2 to 4 build the money and delivery paths independently. Stage 5 is where prescription approval meets payment — deliberately last, so a problem there is a problem in the join, not in the parts.

## Slide 5
Phase 2 — catalogue and WhatsApp commerce
Scaling what we sell, and meeting customers where they already are.
1
Bulk medicine upload
Spreadsheet import for the catalogue, so adding or repricing thousands of products becomes a routine ten-minute operation instead of a project.
Download a template, fill, upload
Dry-run validation before anything saves
Per-row error report, not one vague failure
Audit trail of who imported what, and when
2
WhatsApp buying
Customers order without leaving the chat: send a prescription photo, receive matched medicines with prices, confirm and pay in the same conversation.
Prescription photo straight into OCR
Suggested items with prices in-chat
Confirm and pay without an app install
Reaches customers who never download apps
!
WhatsApp buying depends on Phase 1. Taking payment inside a chat needs the payment and delivery work finished first — it cannot be pulled forward.
Notes: Bulk upload is the higher-certainty item and unblocks the commercial team immediately — it is not dependent on anything in Phase 1. WhatsApp buying is the larger opportunity but strictly downstream of payments; be clear about that dependency so it does not get promised early.

## Slide 6
Current research
Four open evaluations. Each is being compared against the alternatives on cost, coverage and fit before we commit.
A
Payment gateway
COMPARING
Razorpay · Cashfree · PayU · PhonePe PG
DECIDING ON
Approval for the pharmacy category, whether UPI supports a hold-then-capture flow, settlement cycle, and effective cost per transaction.
B
Logistics partner
COMPARING
Shiprocket · Delhivery · NimbusPost · Shadowfax
DECIDING ON
Pincode coverage in our catchment, COD remittance cycle, how returns and refused parcels are charged, and cost per shipment at our volume.
C
WhatsApp commerce platform
COMPARING
AiSensy (current) · Interakt · Wati · Cloud API direct
DECIDING ON
Whether payment can complete inside the chat, catalogue and template support, and per-conversation pricing as volume grows.
D
Payment capture model
COMPARING
Pay at checkout · Authorise then capture · Approve then pay
DECIDING ON
Refund exposure on rejected prescription items, drop-off at a second payment step, and which methods actually support holds in India.
Running separately: prescription retention rules and restricted schedules, being confirmed with counsel before the prescription flow goes live.
Notes: Frame these as decisions I am taking, not asks. Each one is a live comparison rather than a preference. A is the only item with calendar risk — gateway approval for a pharmacy merchant category takes weeks, so I want to start onboarding with the leading candidate while the comparison finishes. D depends on a fact we are still confirming with the gateways: whether UPI supports a hold, since UPI will be most of our volume. The regulatory work in the footer is running in parallel and needs a named owner outside engineering.